## Sheet1
ID | Workstream | Task | Owner | Hrs | Duration | Dependencies | Critical?
G1 | Governance | UTSW model release follow-up | Alan / Chloe | 2 | Jun 8-Jul 11 | None | Yes
G2 | Governance | Code license decision | Alan / Serena | 2 | Jun 8-Jun 12 | None | Yes
G3 | Governance | Dataset license decision | Alan / Serena | 2 | Jun 8-Jun 12 | None | Yes
G4 | Governance | Define board structure | Serena / Jeff | 3 | Jun 10-Jun 28 | None | No
G5 | Governance | Identify board candidates | Serena / Jeff / Chloe | 2 | Jun 10-Jul 5 | G4 | No
G6 | Governance | Secure board commitments | Serena / Jeff | 5 | Jun 24-Aug 1 | G5 | No
G7 | Governance | Draft board charter | Alan | 3 | Jun 24-Jul 5 | G4 | No
M1 | Messaging | Surgical messaging draft | Chloe / Dean | 3 | Jun 8-Jun 20 | None | Yes
M2 | Messaging | CS / AI messaging draft | Elaine | 3 | Jun 8-Jun 20 | None | Yes
M3 | Messaging | Ecosystem / vision messaging | Alan | 4 | Jun 8-Jun 20 | None | Yes
M4 | Messaging | Synthesize unified positioning | Alan | 4 | Jun 17-Jun 27 | M1, M2, M3 | Yes
M5 | Messaging | Serena / Jeff review of positioning | Serena / Jeff / Alan | 3 | Jun 24-Jun 30 | M4 | Yes
B1 | Branding | Style guide refinement | Alan | 3 | Jun 17-Jul 3 | M4 | Yes
W1 | Website | Define sitemap/pages | Alan | 3 | Jun 17-Jun 24 | M4 | Yes
W2 | Website | Website copy integration | Alan | 5 | Jun 24-Jul 8 | M5, B1, W1 | Yes
W3 | Website | Build HTML site | Alan | 5 | Jul 1-Jul 11 | W2, B1 | Yes
W4 | Website | Website QA | Alan / Taryn | 2 | Jul 8-Jul 15 | W3 | Yes
W5 | Website | Deploy website | Alan | 1 | Jul 15-Jul 18 | W4 | Yes
C1 | Comms | One-pager refresh | Alan | 3 | Jul 1-Jul 8 | M5, B1 | No
C2 | Comms | Pitch deck style refresh | Alan | 4 | Jul 1-Jul 11 | M5, B1 | No
S1 | Social | Create LinkedIn page | Taryn / Aviona | 2 | Jun 17-Jun 24 | M4 | No
S2 | Social | Populate LinkedIn page | Taryn / Aviona | 3 | Jun 24-Jul 5 | S1, B1 | No
GH1 | GitHub | Create GitHub org | Elaine | 2 | Jun 10-Jun 14 | G2 | Yes
GH2 | GitHub | Define repo architecture | Elaine | 2 | Jun 14-Jun 21 | GH1 | Yes
GH3 | GitHub | Set permissions / protections | Elaine | 2 | Jun 21-Jun 28 | GH2 | Yes
GH4 | GitHub | Create README / template structure | Elaine | 3 | Jun 24-Jul 5 | GH2 | Yes
HF1 | Hugging Face | Create HF organization | Taryn | 2 | Jun 10-Jun 14 | None | Yes
HF2 | Hugging Face | Configure HF org structure | Taryn | 3 | Jun 14-Jun 21 | HF1 | Yes
HF3 | Hugging Face | Upload shell pages / placeholders | Taryn | 4 | Jun 21-Jul 5 | HF2, M4 | No
MD1 | Models | STEPS checkpoint identified | Elaine | 1 | Jun 17-Jun 21 | GH2, G1 | Yes
MD2 | Models | STEPS code cleanup/package | Elaine | 2 | Jun 21-Jul 3 | MD1 | Yes
MD3 | Models | STEPS validation run | Elaine | 2 | Jul 1-Jul 8 | MD2 | Yes
MD4 | Models | ERRORS checkpoint identified | Elaine | 1 | Jun 17-Jun 21 | GH2, G1 | Yes
MD5 | Models | ERRORS code cleanup/package | Elaine | 2 | Jun 21-Jul 3 | MD4 | Yes
MD6 | Models | ERRORS validation run | Elaine | 2 | Jul 1-Jul 8 | MD5 | Yes
MD7 | Models | Parkland checkpoint identified | Elaine | 1 | Jun 17-Jun 21 | GH2, G1 | Yes
MD8 | Models | Parkland code cleanup/package | Elaine | 2 | Jun 21-Jul 3 | MD7 | Yes
MD9 | Models | Parkland validation run | Elaine | 2 | Jul 1-Jul 8 | MD8 | Yes
MD10 | Models | MC1 checkpoint identified | Elaine | 1 | Jun 24-Jun 28 | GH2, G1 | Yes
MD11 | Models | MC1 code cleanup/package | Elaine | 2 | Jun 28-Jul 8 | MD10 | Yes
MD12 | Models | MC1 validation run | Elaine | 2 | Jul 8-Jul 15 | MD11 | Yes
MD13 | Models | MC2 checkpoint identified | Elaine | 1 | Jun 24-Jun 28 | GH2, G1 | Yes
MD14 | Models | MC2 code cleanup/package | Elaine | 2 | Jun 28-Jul 8 | MD13 | Yes
MD15 | Models | MC2 validation run | Elaine | 1 | Jul 8-Jul 15 | MD14 | Yes
A1 | Annotations | Inventory annotation files | Elaine | 2 | Jun 21-Jun 28 | GH2 | Yes
A2 | Annotations | Validate annotation formats | Elaine | 2 | Jun 28-Jul 8 | A1 | Yes
A3 | Annotations | Cleanup/package annotations | Elaine | 2 | Jul 5-Jul 15 | A2 | Yes
A4 | Annotations | Upload annotations | Elaine | 2 | Jul 15-Jul 20 | A3, GH3, HF2 | Yes
D1 | Docs | Draft GitHub README | Elaine | 1 | Jul 1-Jul 11 | GH4, M5 | Yes
D2 | Docs | Draft model cards | Elaine | 2 | Jul 8-Jul 25 | MD3, MD6, MD9, MD12, MD15 | Yes
D3 | Docs | Draft dataset cards | Elaine | 2 | Jul 15-Jul 25 | A3 | Yes
D4 | Docs | Access instructions | Alan / Aviona | 4 | Jul 8-Jul 18 | V5 | Yes
D5 | Docs | Final documentation QA | Taryn / Alan | 5 | Jul 25-Aug 5 | D1, D2, D3, D4 | Yes
V1 | Videos | Inventory videos | Alan / Aviona | 2 | Jun 17-Jun 28 | None | Yes
V2 | Videos | Decide hosting platform | Alan / Aviona | 2 | Jun 17-Jul 1 | G3 | Yes
V3 | Videos | Define folder structure | Alan / Aviona | 1 | Jun 28-Jul 5 | V1, V2 | Yes
V4 | Videos | Upload videos | Alan / Aviona | 4 | Jul 5-Jul 18 | V3 | Yes
V5 | Videos | Define access workflow | Alan / Aviona | 2 | Jul 8-Jul 18 | V2 | Yes
V6 | Videos | Pressure test video access | Alan / Aviona | 4 | Jul 18-Jul 31 | V4, V5 | Yes
L1 | Leaderboard | Define benchmark datasets | Elaine | 2 | Jul 1-Jul 11 | MD3, MD6, MD9, MD12, MD15 | Yes
L2 | Leaderboard | Define evaluation metrics | Elaine | 2 | Jul 1-Jul 11 | L1 | Yes
L3 | Leaderboard | Generate baseline results | Elaine | 1 | Jul 11-Jul 25 | L2, MD validations | Yes
L4 | Leaderboard | Build HF leaderboard | Elaine | 2 | Jul 18-Aug 1 | L3, HF2 | Yes
L5 | Leaderboard | Test submission workflow | Elaine / Taryn | 2 | Aug 1-Aug 8 | L4 | Yes
APP1 | Web App | UI/UX review of current app | Yunchai / Alan | 8 | Jun 10-Jun 21 | None | Yes
APP2 | Web App | UI/UX redesign | Yunchai | 12 | Jun 17-Jul 8 | APP1, M4 | Yes
APP3 | Web App | Modular architecture design | Yeonjae | 20 | Jun 17-Jul 5 | APP1 | Yes
APP4 | Web App | Refactor architecture | Yeonjae | 15 | Jul 1-Jul 25 | APP3 | Yes
APP5 | Web App | Model integration layer | Yeonjae | 15 | Jul 11-Aug 1 | APP4, MD validations | Yes
APP6 | Web App | Web app internal testing | Yunchai / Brian | 4 | Aug 1-Aug 8 | APP5 | Yes
APP7 | Web App | Web app documentation | Yunchai | 3 | Aug 1-Aug 8 | APP5 | No
INF1 | Inference | Upload workflow | Alan / Yunchai | 5 | Jul 1-Jul 18 | APP2 | Yes
INF2 | Inference | Inference workflow | Alan / Yeonjae | 6 | Jul 8-Jul 25 | APP4 | Yes
INF3 | Inference | Results visualization | Yeonjae | 3 | Jul 18-Aug 1 | INF2 | Yes
INF4 | Inference | Inference testing | Brian | 4 | Aug 1-Aug 8 | INF1, INF2, INF3 | Yes
INF5 | Inference | Inference documentation | Alan / Yunchai | 3 | Aug 1-Aug 8 | INF1, INF2, INF3 | No
P1 | Pubs | MC2 Delphi manuscript completion | Aviona / Jeff | 8 | Jun 17-Jul 5 | None | Yes
P2 | Pubs | MC2 Delphi author review | Aviona / Jeff | 5 | Jul 5-Jul 25 | P1 | Yes
P3 | Pubs | MC2 Delphi arXiv/submission | Aviona / Jeff | 3 | Jul 25-Aug 8 | P2 | Yes
P4 | Pubs | MC2 manuscript completion | Josiah / Alfred | 12 | Jun 17-Jul 8 | None | Yes
P5 | Pubs | MC2 author review | Josiah / Alfred | 6 | Jul 8-Jul 31 | P4 | Yes
P6 | Pubs | MC2 arXiv/submission | Josiah / Alfred | 3 | Aug 1-Aug 15 | P5 | Yes
P7 | Pubs | Tool tracking manuscript completion | Alfred / Jeff | 12 | Jun 17-Jul 8 | None | Yes
P8 | Pubs | Tool tracking author review | Alfred / Jeff | 6 | Jul 8-Jul 31 | P7 | Yes
P9 | Pubs | Tool tracking arXiv/submission | Alfred / Jeff | 3 | Aug 1-Aug 15 | P8 | Yes
P10 | Pubs | Needs finding manuscript completion | Chloe | 10 | Jun 17-Jul 8 | None | Yes
P11 | Pubs | Needs finding author review | Chloe | 5 | Jul 8-Jul 31 | P10 | Yes
P12 | Pubs | Needs finding arXiv/submission | Chloe | 3 | Aug 1-Aug 15 | P11 | Yes
QA1 | Release QA | End-to-end user journey test | Alan / Taryn / Aviona | 4 | Aug 5-Aug 10 | W5, D5, V6, L5, APP6, INF4 | Yes
QA2 | Release QA | Fix final blockers | Alan / Elaine / Yeonjae | 4 | Aug 8-Aug 13 | QA1 | Yes
LA1 | Launch | Launch readiness review | Alan / Serena / Jeff | 3 | Aug 13-Aug 14 | QA2, P submissions | Yes
LA2 | Launch | Public launch | Alan / Team | 2 | 2026-08-15 | LA1 | Yes